Strategic Plan to District Scorecard, 2018

Prepared for Barrington Public Schools

|  |  |  |
| --- | --- | --- |
|  | **Administrators** | **School Committee** |
| **May** | * Post plan to website
* Press release on completion of planning process
* Develop brand/ visuals
* Draft annual district scorecard and share with School Committee (5/31)
 | * Self-assessment and goal-setting around norms/ benchmarks
* Review of draft scorecard in progress (5/31)
 |
| **June** | * June 6: meet with School Committee to review and finalize draft annual district scorecard\*
* Align School Improvement Plan template to scorecard
* June 14, present 2017-2018 School Improvement Plan results

\*some goals will need to await results to set an improvement target | * June 6: meet with Admins to review and finalize draft annual district scorecard\*
* Develop annual meeting agenda that reflects progress monitoring of key pillar goals
* Develop School Committee scorecard (if desired)
* June 14, review 2017-2018 School Improvement Plan results
 |
| **July** | * Prepare for rollout of strategic plan in Back to School communications
 |  |
| **August** | * Rollout new strategic plan in newsletters, Back to School events, publicity
* School Improvement Teams continue School Improvement Planning with new data
 | * Rollout strategic plan and annual agenda plan with community through meetings and press coverage
* Rollout School Committee scorecard (if desired)
 |
| **September- October** | * Share final annual district scorecard with all targets with School Committee (workshop)
* Share aligned School Improvement Plans with School Committee (workshop)
 | * Implement annual meeting agenda that reflects progress monitoring of key pillar goals and “business” at all other sessions
* Engage with final annual district scorecard and School Improvement Plans (workshop)
 |
| **December - January** | * Prepare for 1st progress monitoring – validating implementation of actions and reporting any adjustments needed based on progress monitoring data (workshop)
 | * Engage with progress monitoring – validating implementation of actions and reporting any adjustments needed based on progress monitoring data (workshop)
 |