Strategic Plan to District Scorecard, 2018

Prepared for Barrington Public Schools

|  |  |  |
| --- | --- | --- |
|  | **Administrators** | **School Committee** |
| **May** | * Post plan to website * Press release on completion of planning process * Develop brand/ visuals * Draft annual district scorecard and share with School Committee (5/31) | * Self-assessment and goal-setting around norms/ benchmarks * Review of draft scorecard in progress (5/31) |
| **June** | * June 6: meet with School Committee to review and finalize draft annual district scorecard\* * Align School Improvement Plan template to scorecard * June 14, present 2017-2018 School Improvement Plan results   \*some goals will need to await results to set an improvement target | * June 6: meet with Admins to review and finalize draft annual district scorecard\* * Develop annual meeting agenda that reflects progress monitoring of key pillar goals * Develop School Committee scorecard (if desired) * June 14, review 2017-2018 School Improvement Plan results |
| **July** | * Prepare for rollout of strategic plan in Back to School communications |  |
| **August** | * Rollout new strategic plan in newsletters, Back to School events, publicity * School Improvement Teams continue School Improvement Planning with new data | * Rollout strategic plan and annual agenda plan with community through meetings and press coverage * Rollout School Committee scorecard (if desired) |
| **September- October** | * Share final annual district scorecard with all targets with School Committee (workshop) * Share aligned School Improvement Plans with School Committee (workshop) | * Implement annual meeting agenda that reflects progress monitoring of key pillar goals and “business” at all other sessions * Engage with final annual district scorecard and School Improvement Plans (workshop) |
| **December - January** | * Prepare for 1st progress monitoring – validating implementation of actions and reporting any adjustments needed based on progress monitoring data (workshop) | * Engage with progress monitoring – validating implementation of actions and reporting any adjustments needed based on progress monitoring data (workshop) |